## Slide 1: GBCS 4.1 Programme Initial Pallet Validation (IPV)
We believe in making Britain more connected, so we can all lead smarter, greener lives.

## Slide 2
 | Release | RAG | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
 | Dependencies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1 | TOSH |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | EDMI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3 | WNC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2023
2022
2024
CPL
TAB
20/07
TAG
30/08
CPL
10/11
DB UIT
Holiday
EOC
CPA Certification
CPA Certification
PIT - 1
SIT SB. DB
UP
Pilot
(OTA)
In Supply Chain
TAB
Feb
SB UIT
29/08 – 10/10
OA
OA
PPMID Meter Device Ava.
PIT -2
PPMID Conf Test
TAG Approval of TAD
Test Approach Doc
CSP System Changes. To test GBCS 4.1 CH FW.
14/06
Start UIT engagement with Customers TOSH
PIT -3
(Prod fix fw 4.1.0.4)
CPL
CPL
DB. DB-F UIT
TAB
10/03
TAG
29/03
CPL
14/07
TAB
23/05
TAG
28/06
CPL
15/09
DB UIT
OA
PIT (Prod Fix fw 13.6)
Defect fix
PIT (CPA related Fix)
Defect Fix
CPA Certification
TAB
Oct
UP
SB UIT
Pilot (OTA)
In Supply Chain
OA
SIT SB. DB &
SB UIT
UP
SIT SB. DB. DB-F
OA
Pilot (OTA)
OA
In Supply Chain
PIT -1
TAB
Oct
03/07 – 14/08
PIT -1
PIT -2
22/04
19/02
29/03 – 15/05
ECOS / June 23
Go Live
GBCS 4.1 Plan on a page – Proposed for February 2023, OPSG (88_1402) Meeting
Notes: The top headline is, the Programme of work is on track, and progressing within the agreed JIP Milestone dates. However, a change to the running order is being proposed.
The TOSH Release is tracking ahead of schedule, and therefore being proposed to move to position 1 on the plan. This also means that we will be expediting the TAB, TAG and UIT dates for TOSH. I’ll be covering further details on the next slide.
The EDMI release will move down from Position 1 to Position 2. This is as a result of CPA related changes (from GBCS 3.2) being identified by EDMI’s test house that need to be applied to GBCS 4.1 code base, in order for the CPA certification to be achieved. The date changes have not impacted the JIP Milestone dates.
WNC is tracking plan.

## Slide 3
 | Release | RAG | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
 | Toshiba Plan without First Pallet |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Toshiba Plan with First Pallet |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | EDMI Plan without First Pallet |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | EDMI Plan with First Pallet |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | WNC Plan without First Pallet |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | WNC Plan with First Pallet |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2024
2023
2025
Holiday
CPL
CPL
14/07
DB UIT
OA
SB UIT
Pilot (OTA)
OA
CPL
CPL
14/07
DB UIT
OA
SB UIT
Pilot (OTA)
In Supply Chain
OA
19/02
1st Pallet Del
1st Pallet
Delivered
1st Pallet
Installed
OA
GBCS 4.1 – IPV Indicative Schedule Impact
1st Pallet Install (3m)
CPL
CPL
DB UIT
CPL
15/09
CPL
10/11
DB UIT
SB UIT
OA
Pilot (OTA)
OA
In Supply Chain
Pilot
(OTA)
In Supply Chain
SB UIT
OA
OA
14/06
22/04
CPL
CPL
15/09
DB UIT
OA
SB UIT
Pilot (OTA)
In Supply Chain
OA
30/10
1st Pallet Manu
1st Pallet
Delivered
1st Pallet
Installed
OA
1st Pallet Install (3m)
CPL
CPL
10/11
DB UIT
Pilot
(OTA)
SB UIT
OA
OA
In Supply Chain
30/01
1st Pallet Manu
1st Pallet
Delivered
1st Pallet
Installed
OA
1st Pallet Install (3m)
Holiday
Mass OTA Deployment
Mass OTA Deployment
Mass OTA Deployment
Mass OTA Deployment
Mass OTA Deployment
Mass OTA Deployment
In Supply Chain
30/09
Notes: The slide shows the plan with and without 1st Pallet covering all CH variants. I’ll cover the some planning principles and considerations on a way forward before opening up for comments from the group
The planning principles of 1st pallet include
The Decision to manufacture 1st pallet will be made following a successful OTA Pilot by DCC Operations.
The Mass OTA deployment will continue along side the 1st pallet delivery
There are approx. 3 months allowed for the 1st pallet delivery
The 1st pallet install phase is proposed to be 3 months to allow customers to reach confident level of volumes prior to a decision to Mass Manufacture.
Each Pallet contains 896 CHs per variant, which would need to be distributed across the customer base to gain greater HAN diversity
DCC criteria for 1st Pallet requires at least 50% installation rate within 3 months to progress to a decision of Mass Manufacture
In terms of a way forward, from a cost, schedule vs benefits it makes sense to consider
1st Pallet validation on the SB Variants for WNC and EDMI
Because functionally DB and SB have a similar code base
SB production volumes are higher
We are not recommending TOSH SB & DB CHs as this will be transitioning to the 4G at some point, (in 2024)
This will also result in cost reductions for 1st Pallet
And On balance will allow for TOSH JIP Milestones to be maintained and as well as EDMI and WNC DB JIP milestones to be maintained
We wanted to get customers view and support on the recommendation –

## Slide 4: Comms Hub Manufactures and Variants
Overview
2 CSPs
3 CH manufactures
7 CH variants in scope for test:
  Single Band x3 (EDMI, WNC & TOSH)
  Dual band x3 (EDMI, WNC & TOSH)
  Dual Band Fylingdales x1 (EDMI)
Large volume of standard UIT variants are also tested
Arqiva (North)
VMO2 (Central and South)
WNC
EDMI
SB
DB
DB-F
SB
DB
TOSH
SB
DB
CSP
CSP Supplier
CH Variants
UIT Variants
RTL & Debug
Wireless ITCH
RTL & Debug
Wired ITCH
Wireless ITCH
RTL & Debug
RTL & Debug
RTL & Debug
Wired ITCH
Wireless ITCH
RTL & Debug
Wireless ITCH
RTL & Debug
Wired ITCH
Wireless ITCH
Wireless ITCH
MESH
RTL & Debug
MESH
RTL & Debug
Notes: In the previous slide we covered the size and content of the release.
The diagram shows the scale and complexity of the functionality and fixes that need to be applied across the CSP landscape for GBCS release.
Therefore the planning needs to include all these components.
This covers (go to Overview)
Debug goes through PIT -> SIT -> UIT proving -> UIT (Non-Debug for Arqiva too)
Non-Debug (RTL) goes through PIT -> UIT Proving -> UIT
Wireless ITCH goes through PIT -> UIT Proving -> UIT
Wired ITCH goes through PIT -> Meter Manufacturers
Please rename RTL as “RTL & Debug”
Wired ITCH exist only for DBCH.
No Wireless ITCH for DBCH-F
Yes, if you want to capture MESH as well they have just for Tosh SB Mesh, DB Mesh & each Mesh has got Debug & RTL.
Mesh don’t have Wireless & Wired ITCH. Mesh testing follows PIT -> UIT Proving -> production (I’m not so sure how much testing UIT proving does).